## Sheet1
Project | Phase | Activity | Start | End | Gate
Project A | Preparation | Preparation | 2024-07-01 | 2025-03-30 | G1
Project A | Pre-study | Pre-study | 2025-04-01 | 2025-09-30 | G2
Project A | Establishment | Establishment | 2025-10-01 | 2025-10-30 | G3
Project A | Implementation | Implementation | 2025-11-01 | 2025-12-30 | G4
Project A | Stock build-up | Stock build-up | 2026-01-01 | 2026-06-30 | G5
Project A | Closure | Closure | 2026-07-01 | 2026-12-15 | G6
Project B | Preparation | Preparation | 2024-07-01 | 2025-03-30 | G1
Project B | Pre-study | Pre-study | 2025-04-01 | 2025-09-30 | G2
Project B | Establishment | Establishment | 2025-10-01 | 2025-10-30 | G3
Project B | Implementation | Implementation | 2025-11-01 | 2025-12-30 | G4
Project B | Stock build-up | Stock build-up | 2026-01-01 | 2026-06-30 | G5
Project B | Closure | Closure | 2026-07-01 | 2026-12-15 | G6
Project C | Preparation | Preparation | 2024-07-01 | 2025-03-30 | G1
Project C | Pre-study | Pre-study | 2025-04-01 | 2025-09-30 | G2
Project C | Establishment | Establishment | 2025-10-01 | 2025-10-30 | G3
Project C | Implementation | Implementation | 2025-11-01 | 2025-12-30 | G4
Project C | Stock build-up | Stock build-up | 2026-01-01 | 2026-06-30 | G5
Project C | Closure | Closure | 2026-07-01 | 2026-12-15 | G6

## Sheet2
Project | Phase | Activity | Start | End
TP | WP1 | Cemented carbide designs | 2024-09-01 | 2024-12-15
TP | WP2 | Trials C700-X | 2024-03-15 | 2024-06-15
TP | WP2 | Trials C710-X | 2024-08-20 | 2024-10-10
TP | WP2 | Mfg. | 2024-10-20 | 2024-11-10
TP | WP2 | Cutting tests | 2024-11-15 | 2025-01-30
TP | WP3 | Planning + Mfg | 2024-10-20 | 2024-12-15
TP | WP3 | Cutting tests | 2025-02-01 | 2025-02-28
TP | WP4 | Preparation | 2024-11-01 | 2025-02-15
TP | WP4 | Mfg. | 2025-03-01 | 2025-06-01
TP | WP4 | Test Period | 2025-06-15 | 2025-11-30
TP | Gate | RoR + IMTM | 2025-11-15 | 2025-12-15
TP | Gate | PLR + Pre-RDC + RDC | 2026-01-10 | 2026-03-28